## Sheet1
Timeline and Timeframe Assignments 3 & 5
| Course Semester |  |  |  |  | End of Semester | Outside course semester
| 2021-10-17 | 2021-10-24 | 2021-10-31 | 2021-11-07 | 2021-11-14 | 2021-11-21 | 2021-11-28 | 2021-12-05 | 2021-12-12 | 2021-12-19 | 2021-12-26 | 2021-01-02 | 2021-01-09 | 2021-01-16 |  | 2021-01-23 | 2021-01-30
| Week 7 | week 8 | week 9 | week 10 | week 11 | week 12 | Week 13 | week 14 | week 15 | weel 16 | week 17 | week 18 | week 19 | week 20 |  | week 21 | week 22
Task & Hours breakdowns
| Task |  | Area |  | Time allocated (hrs) | Project Leaders | [8 empty] | Group Member |  | Assigned Hrs
| Group Process |  | Team profile |  | 3.6 | Taylen | [8 empty] | Taylen |  | 28.85
| Career plans |  |  |  | 3.6 | Taylen | [8 empty] | Ahmet |  | 7.5556
| GitHub organisation |  | Tools |  | 1.8 | Taylen | [8 empty] | Tetsu |  | 36
| Additional Tools/MS Teams/ETC |  |  |  | 1.8 | Taylen | [8 empty] | Hugo |  | 29.1
| Report on Efficacy of tools |  |  |  | 3.6 | Taylen | [8 empty] | Tim |  | 45
| Overview |  | Project Plan |  | 4 | [9 empty] | Brandon |  | 36
| Aims |  | Project Plan |  | 68 | Tim
| Plans and Progress |  |  |  |  | Tim
| Roles |  |  |  |  | Hugo
| Scopes and Limits |  |  |  |  | Tim
| Tools and Technologies |  |  |  |  | Ahmet
| Testing |  |  |  |  | Tim
| Timeframe |  |  |  |  | Tim
| Risks |  |  |  |  | Tim
| Group Process & Comms |  |  |  |  | Taylen
| Analysis of Jobs to Perform |  | Skills & Jobs |  | 2 | Hugo
| Job Advertisement #1 |  | Skills & Jobs |  | 4.9 | Hugo
| Job Advertisement #2 |  |  |  | 4.9 | Hugo
| Job Advertisement #3 |  |  |  | 4.9 | Hugo
| Job Advertisement #4 |  |  |  | 4.9 | Hugo
| Feedback |  | Group |  | 1.8 | Group
| Group Reflection |  | Group |  | 1.8 | Group
| PDF Report |  | Presentation |  | 7.2 | Taylen
| Website |  |  |  | 7.25 | Taylen
| Storyboard |  | Assignment 5 |  | 14.4 | Brandon & Tetsu
| Script |  |  |  | 28.8 | Brandon & Tetsu
| Video |  |  |  | 28.8 | Brandon & Tetsu
| Total Hours |  |  |  | 198.05
| Total hours per person |  |  |  | 33.0083